## Slide 1: Workshop 3: Improving Project Estimates and Communication
PA TechCon
May 4, 2017

## Slide 2: Agenda
  About Estimates
  Estimation Methodologies
  Best Practices
  Team Exercise

## Slide 3: Estimates v. Commitments
Requestors usually don’t know the difference…
  The Problem with Estimating Too High
    Could lose a bid
    Project canceled for lack of overestimated funds
    Rejection of a good solution
    Long term loss of credibility
  The Problem with Estimating Too Low
    Missed deadlines
    Lose money on bid
    Setup for failure
    Over budget
    Long term loss of credibility

## Slide 4: What Are We Estimating?
What will it take to complete a project? What are we estimating?
Requirements
Work Breakdown Structure
Implementation Process & Tasks
Effort
Resource
Costs
Duration
Material
Costs
Microsoft Word
& Other WBS Tools

## Slide 5: Document All Assumptions
Document all assumption and their impact on the estimate.
  Clarifies the thought processes (for yourself and others)
  Provides a disclaimer for estimates that are not “perfect predictions”
  May calm the fears of those providing an estimate
Deliver all the Assumptions in detail with the estimate.
Accept that you won’t have every detail – it’s not realistic or necessary.

## Slide 6: Typical Assumptions
  Scope of Work
    Functionality
    Performance & Capacity
    Security
  Available Staff & Skills
  Tools & Technologies
  SDLC Phases (Testing, Training, Documentation)
  Availability and Quality of Data
  Timing
  Dependencies on Other Participants
  Available Facilities
  Procurement Timing
  Work Hours
  Turnaround on Review and Approval of Artifacts

## Slide 7: Effort Does Not Equal Duration
Many factors impact a resource’s availability and effectiveness.
  Other Project Commitments
  Meetings
  Personal Distractions
  Vacations
  Holidays
  The Toolkit includes an adjustable factor for Hours/Day. Default = 7.5
MS Project and other tools allow you to create calendars and adjust availability of resources.

## Slide 8: Communicate the Complete Estimate
Communicate the estimate as a complete package that documents and highlights all information.
  Scope
  Approach
  Effort & Duration
  Material Costs
  Assumptions & Risks
  Range of Results
Summarize on one page along with the details.

## Slide 9: Estimation Methodologies

## Slide 10: Expert Judgement
The most common approach to estimation can be incredibly accurate and can be substantially abused.
  Find Real Experts – with Hands-on Experience
  Make Sure Requirements are Clearly Understood

## Slide 11: WBS Focused
Top-down
  Develop Level Of Effort from the top of the WBS. Example:
    Estimate for the Infrastructure
    Divide the Infrastructure into components and validate
  Leverage work breakdown structure and data from previous projects
  Pro: Good for First Pass
  Con: Lacks Detailed Justification
Bottom Up
  Develop Level of Effort from the bottom of the WBS. Example:
    Estimate for each Server
    Roll up all the estimates
  Pro: Detailed
  Con: Requires additional time and detail, easy to get exaggerated results if not careful
  When to use top down…
  The early stages of a project to develop talking points for management
  When you have similar projects for comparison
  When time to develop an estimate is limited
  When high level budgetary estimates are needed to obtain funding

## Slide 12: Parametric Model
Leverage comparative or analogous projects to create a model.
  Extrapolate WBS components - Understand what may change
    Resources skills
    Complexity
    Customer
    Size
  Based on repeatable projects and work packages
  Uses scalable results to create new estimates
  Pro: fairly accurate if refined carefully over time, variations can be measured
  Con: takes time to build up model, many variations/parameters

## Slide 13: Delphi
Delphi is a consensus building exercise where experts provide estimates and the results are shared anonymously as input to another round of estimates.
1st Round
Analysis of Results
2nd Round
Analysis of Results
3rd Round
Analysis of Results
Feedback
Feedback
Feedback

## Slide 14: PERT (Program Evaluation and Review Technique)
The Beta Distribution analysis allows estimators to consider a range of outcomes.
  Estimate = (Optimistic + 4 * Expected + Pessimistic)/6
  Consider multiple estimators
  Allows for the analysis of total optimistic and pessimistic scenarios
  The beta distribution estimation technique is used when there is a degree of uncertainty around expected durations of a work breakdown structure element.

## Slide 15: Best Practices
  Document Assumptions
  Create a WBS
  Get Broad Participation
  Learn From History
  Compare Estimates
  Effort Does Not Equal Duration
  Follow a Process
  Communicate the Whole Estimate

## Slide 16: Team Exercise

## Slide 17: What Will it Take to Build a Shed in Steve’s Backyard
Shed Requirements
  Dimensions 12 ft. x 12 ft.
  Door – 6’ entry
  Window
  Vents
  Lock
  Ramp
  No electricity
Your Table is Your Team.
What Questions Do You Have About The Scope?

## Slide 18: Exercise
  Clarifying Scope
    What Questions Might We Ask?
    Class Discussion – 5 Minutes
  Developing WBS
    Team Collaboration – 5 Minutes
    Class Discussion – 5 Minutes
  Developing & Estimating Tasks
    Team Collaboration Complete Worksheet – 15 Minutes
    Class Discussion – 10 Minutes

## Slide 19: Realistic Scope Questions…
Scope
  Need Permits?
  Concrete Pad or Wooden Floor?
  Height? Includes Loft?
  Framing Spacing?
  Weight Capacity?
  Exterior Finish?
  Gutters?
  Trim work and Decorations?
Approach
  DIY, Contractor, Kit, Pre-Built?
  Accounting for waste/scrap?
  Cleanup and disposal?
  What’s the weather/season?

## Slide 20: Create a Work Breakdown Structure
  Site Plans & Building Design
  Permit
  Concrete Pad (or footings)
  Frame
  Siding/Sheathing
  Roof
  Window
  Door
  Finished/Painted Exterior
  Inspection Certificate

## Slide 21: Implementation Tasks
  Develop Plans
  Obtain Permit
  Buy Materials
  Build Foundation
  Build Frame
  Attach Siding/Sheathing
  Build Roof
  Install Window
  Install Door
  Finish Exterior (Paint, Trim, etc.)
  Inspection

## Slide 22: Contact Information
For more information regarding this presentation please contact:
Steven E. Young, PMP, Vice President
syoung@mathtechinc.com
Frank Nestore, PMP, Director
syoung@mathtechinc.com
Mathtech, Inc.
Mathtech, Inc.
2465 Kuser Road
Suite 200
Hamilton, NJ 08690
Phone: 609-689-8520
www.mathtechinc.com